## objectives
Main objective of the KT
Mr. Shivalingam Narsanolla comes to the Netherlands for an IT training to follow for front-end applications for the ABN AMRO Channels Department . Mr. Shivalingam Narsanolla follows a 80 days training at ABN AMRO training facilities to acquire knowledge of customer specific implementations of the software so that when he returns to India he can perform development and maintenance activities.
How will the learned topics be developing the business in India?
He will return to india and not only perform the tasks assigned to him in the short term, but, also assist in onboarding new team members in India. Eventually as the experience grows, he will be able to guide the new members effectively. This can replace the onborading/training that is done onsite by doing it offshore.
What are the learning goals?
The associate sould be able to perform the tasks assigned to him independently. He should understand the overall bussiness and architecture of the project. He should understand the way of working, process and tools used in the project.

## KT Plan
Knowledge Transfer Plan:
Knowledge Transfer Plan for Capgemini
Name | Shivalingam Narsanolla
Duration | 80 days
Serial No. | Activity Name | Description | Participants | Trainer | Status | Timelines
1 | Introduction training | Introduction ABN AMRO Channels Internet, Mobile & Intranet Development environment & Front End Architecture. Also short tour through building and introduction to key players |  | Moest, Matijs | Not Started | 2018-08-06
2 | Front-end development standards, tooling, libraries, QA, testing | Training on existing ABN AMRO front-end development standards, tooling, libraries, QA procedures and testing cycles |  | Moest, Matijs, Oliver Verver | Not Started | 11-06-2018 till 15-06-2018
3 | Hands on training Coding standards | Overview of Coding standards and Sonar |  | Oliver Verver | Not Started | 18-06-2018
4 | Backbase training | Training Backbase Portal - 5 day external training provided by Backbase |  | Matijs Moest | Not Started | 19-06-2018 to 29-06-2018
5 | Deployment and release management | Training on deployment & release management process in the ABN AMRO DTAP environment |  | Johan Markenstein & Jos Rutte | Not Started | 02-07-2018 to 06-07-2018
6 | Hands on training on Fiscal Savings Fucntionality | Introduction to Fiscal Savings functionality and widget development |  | Lead Developer teams | Not Started | 09-07-2018 to 13-07-2018
7 | Customer Portal and Employee Portal | Introduction training to the Backbase portal environment and Widget Configuration Procedures (including hands-on exercises) |  | Moest, Matijs | Not Started | 16-07-2018 to 18-07-2018
8 | Hands on training on Fiscal Savings Architcture | Introduction to Fiscal Savings and widget development |  | Lead Developer teams | Not Started | 19-07-2018, 20-07-2018
9 | Project Specific Knowledge Transfer | Introduction to Fiscal Savings functionality and widget development |  | Floris, Rabia | Not Started | 23/07/2018
10 | Project Specific tools training | Introduction to the tools used in development of the project (FS) |  | Henk, Patrick | Not Started | 24/07/2018
11 | Hands on training GPS | GPS functional overview |  | Lead Developer GPS team | Not Started | 25-07-2018 to 31-07-2018
12 | Recap Training Sessions | 1. Discuss the understanding 2. Discuss the gaps, alternatives 3. Plan next training |  | Lead Developer, Moest, Matijs | Not Started | 01-08-2018 to 09-08-2018
13 | Exam & Fun Event | Short examination to assess build up knowledge & fun event in Amsterdam |  | All | Not Started | 2018-10-07
14 | Knowledge transfer: Maintenance and Support | Functional Usage of Application 1. The business processes addressed by the application(s) in scope. 2. Any current pain points 3. Future plans |  | Lead Developer, scrum master | Not Started | 13-08-2018 till 22-08-2018
15 | On-the-job training | Work together with lead developers to 1. Resolve issues, bugs 2. Learn tasks of daily support and use of required tooling 3. On-the Job training 4. Frequency of reporting to business/IT. 5. Metrics to be reported |  | Lead Developer, scrum master | Not Started | 23-08-2018 to 31-08-2018
Objectives
Mr. Shivalingam Narsanolla comes to the Netherlands for an IT training to follow for front-end applications for the ABN AMRO Channels Department . Mr. Shivalingam Narsanolla follows a 80 days training at ABN AMRO training facilities to acquire knowledge of customer specific implementations of the software so that when he returns to India he can perform development activities.